## Sheet1
|  | Oct |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  |  | Mar
| Week Commencing: | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 7 | 14 | 21
Electronics
Sensor PCB design | bar: Oct 19 to Nov 2; Dec 7 to Dec 21
Sensor PCB assembly | bar: Nov 2 to Dec 7; Dec 21 to Jan 4
Quadcopter electronics assembly | bar: Nov 9 to Dec 7; Jan 4 to Jan 18
Camera system assembly | bar: Nov 9; Jan 18 to Jan 25
Full can assembly | bar: Nov 23 to Dec 21; Jan 25
Software
Write libraries for sensor | bar: Oct 19 to Dec 14
Write libraries for RF98W | bar: Nov 9 to Nov 23
Write Can code | bar: Nov 23 to Dec 21; Jan 4 to Jan 25
Mechanics
Layer design (using CAD) | bar: Oct 19 to Oct 26; Nov 23 to Dec 7
Arm design (using CAD) | bar: Oct 19 to Nov 2; Dec 21 to Jan 4
Layer manufacture (using 3D printing) | bar: Oct 26 to Nov 9; Jan 11 to Jan 18; Feb 15 to Feb 22
Arm manufacture (using 3D printing) | bar: Nov 2 to Nov 16; Jan 11 to Jan 18; Feb 15 to Feb 22
Manufacture of arm opening system | bar: Nov 23 to Dec 14
Can assembly | bar: Dec 7 to Dec 21; Jan 25; Feb 29
Testing
PCB testing | bar: Nov 23 to Nov 30
Quadcopter system testing | bar: Nov 16 to Nov 30
Camera system testing | bar: Nov 9 to Nov 16
Full electronics testing | bar: Dec 7 to Dec 21
Test arm opening | bar: Dec 14
Flight test | bar: Dec 21 to Jan 25
Launch procedure testing | bar: Feb 1 to Mar 7
Outreach
Fundraising | bar: Oct 19; Jan 4 to Jan 25
Talks to primary school students | bar: Nov 23; Dec 7
Inside school promotion
Base Station
Software | bar: Nov 2 to Feb 8
Communications system design | bar: Nov 9 to Nov 30
Base station electronics design | bar: Jan 4 to Jan 25
Base station electronics manufacture | bar: Jan 25 to Feb 8
Paperwork
Progress Reports | bar: Oct 19 to Oct 26; Nov 16 to Nov 30; Jan 25 to Feb 8
Submission of documentation to sponsors